# Pilot Governance Charter — DCFS ILC AI Rollout

## 1. Purpose

This charter defines how pilot governance operates — who meets, when, what they review, what they decide, what they track, and what artifacts come out. It is the working rulebook for the pilot phase (Sprints PI 26.2.1 → PI 26.2.5, ending on or about July 20).

Phase B (DCFS AI Governance Team for scale) has a separate charter — defined when that team is seated.

## 2. Scope

### In scope for pilot governance

Pilot team: Intact (1 team, 5 roles — Tester, Solution Architect, Business Analyst, Developer, Testing Services Lead)

Tools: GitHub Copilot, Atlassian Rovo, M365 Copilot, D365 Copilot (subject to authorization)

Activities: AI-assisted story writing, acceptance criteria, test generation, code explanation/refactoring, documentation, configuration, code generation (pro code)

Boundaries: SDLC acceleration only — no business logic, domain, or workflow changes

Compliance envelope: DoIT AI Policy (Apr 1, 2025) + NIST AI RMF 1.0 + DCFS data regs (CANTS, CCWIS, FERPA, HIPAA)

### Out of scope for pilot governance

Scaling decisions (those require Phase B — full DCFS AI Governance Team)

New tools beyond the 4 authorized

Changes to agency-level AI policy

Anything touching DCFS case data, PII, or protected state data

## 3. Governance team composition

Recommended minimum viable — 3 DCFS seats, plus 2 vendor roles that report to the team but do not sit on it:

| Role | Name | Status |
| --- | --- | --- |
| Pilot Governance Lead | DCFS designee | TBD (pending David's confirmation) |
| Executive Sponsor | Jim Daugherty (DCFS CIO) | Confirmed |
| Security & Privacy Lead (combines security + data privacy for pilot) | DCFS designee | TBD |
| AI Transformation Lead (reports to — does not sit on team) | Vinay Lagisetty (Krasan) | Confirmed |
| Engagement Director (reports to — does not sit on team) | Emil "Romi" Kovacs (Krasan) | Confirmed |

DoIT: external policy liaison, not a team member. Compliance reports sent up per DoIT AI Policy §4.

## 4. Meeting cadence

| Meeting | Frequency | Duration | Purpose |
| --- | --- | --- | --- |
| Pilot Governance Weekly | TBD | 45 min | Review pilot progress, approve changes, clear blockers |
| Incident response | As needed | 30 min | Safety / compliance incidents — triggered by Pilot Governance Lead |
| Mid-pilot checkpoint | ~Jun 10 | 60 min | Assess pilot health against 10–15% target; adjust if needed |
| Pilot closeout | ~Aug 20 | 60 min | Present results + draft playbooks to Phase B team (once seated) |

## 5. Weekly meeting — what gets reviewed

Each weekly Pilot Governance meeting covers these 6 items in order. Target time per item in parentheses.

**NIST AI RMF alignment:** 5.1 + 5.2 → **MEASURE** · 5.3 → **MAP + MANAGE** · 5.4 + 5.5 → **GOVERN + MANAGE** · 5.6 → **GOVERN**. The weekly agenda operationalizes the four NIST functions in one 45-minute meeting.

### 5.1 Metrics dashboard (10 min)

Weekly delta on active baseline metrics (see §7).

Flag any metric trending wrong direction (>10% decline from baseline).

No deep-dive — that's for mid-pilot checkpoint.

### 5.2 AI output quality spot check (10 min)

Sample 3–5 AI-assisted artifacts from the week (1 story, 1 test, 1 doc, 1 code snippet).

Check: HITL review happened? Quality acceptable? Any drift from guardrails?

Record findings in Spot Check Log (see §7.4).

### 5.3 Risks & blockers (10 min)

Review risk register changes since last week.

New risks flagged by pilot team or AI Transformation Lead.

Action owners + due dates for any mitigation.

### 5.4 Change requests (5 min)

Any pilot team request for: new tool, guardrail adjustment, scope expansion, training tweak.

Approve / defer / deny in the meeting — do not carry over.

Log in Change Request Register (see §7.5).

### 5.5 Compliance check (5 min)

DoIT AI Policy compliance status — any gap surfaced this week?

Explicit check — any prompt-drift incidents? PII, case data, CANTS/CCWIS references, or out-of-scope content in prompts or AI output.

Audit trail spot check (JIRA transitions + GitHub PR history).

Bias / fairness spot check (are AI suggestions reflecting any pattern we should flag?).

### 5.6 Action items + next week (5 min)

Confirm owner + due date for anything new.

Preview next week (training schedule, sprint boundaries, vendor arrivals).

## 6. Decisions in scope for pilot governance

| Decision | Authority |
| --- | --- |
| Approve pilot-scope changes | Pilot Governance Lead (requires CIO for scope expansion) |
| Approve tool access additions within authorized set | Pilot Governance Lead |
| Approve guardrail adjustments | Pilot Governance Lead (log reason + impact) |
| Approve training content changes | Pilot Governance Lead + AI Transformation Lead |
| Halt pilot on safety / compliance concerns | Pilot Governance Lead (notify CIO within 24 hr) |
| Extend pilot timeline | CIO only (Pilot Governance Lead recommends) |
| Add a new tool outside authorized set | CIO only (requires DoIT 30-day notice) |
| Approve a different pilot team / roles | CIO only |

## 7. What we track (artifacts + metrics)

### 7.1 Active pilot metrics

Final set locked after baseline (Apr 30). Candidate families:

| Family | Metrics |
| --- | --- |
| Delivery | sprint velocity · cycle time · throughput · sprint predictability |
| Quality | story quality score (QUS) · story rejection rate · first-pass yield · test coverage · defect density |
| Efficiency | story review cycle time · test creation time · documentation coverage |
| Team health | SPACE survey (5-dim) · requirement clarity · AI tool satisfaction |

Measurement philosophy: tangible outputs, not story points. Before/after pilot vs. baseline + control teams.

### 7.2 Risk register

Maintained by the AI Transformation Lead and reviewed weekly in §5.3 (internal working document).

### 7.3 AI tool usage data

During pilot: Read directly from tool admin dashboards (GitHub Copilot, Atlassian Rovo, Microsoft 365 Copilot, Dynamics 365 Copilot). Includes prompt counts, acceptance/rejection rates, and per-user activity. Tool dashboards satisfy DoIT AI Policy §7 monitoring and documentation requirements; no separate manual log required during pilot.

Prompt-drift incidents (PII, case data near-miss, out-of-scope output) are captured via the escalation path in §9 and reviewed in §5.5 Compliance check.

**Flag for full rollout:** If DoIT or DCFS determines that a formal, structured AI usage log is required when the program scales beyond pilot (Phase B — ART-wide rollout), it will be designed and implemented at that time. Not in scope for pilot.

### 7.4 Spot check log

For each weekly sample (see §5.2):

Artifact type (story / test / doc / code)

Reviewer

HITL verification ✅ / ⚠ / ❌

Quality grade (1–5)

Notes / learnings

### 7.5 Change request register

For each CR raised in §5.4:

Date raised

Requested by

Nature of change

Decision (approve / defer / deny)

Decision rationale

Implemented date

### 7.6 Compliance evidence

Kept in the "DCFS AI Rollout" Teams channel (shared tab):

Training completion records (all pilot participants)

AI disclosure acknowledgments

Guardrail doc sign-offs

DoIT 30-day notice + any correspondence

Per-sprint audit trail exports

## 8. Pilot team → governance channel

| Channel | When | Who |
| --- | --- | --- |
| Pilot team daily stand-up flag | Anything urgent (safety, blocker) | Pilot team members → Pilot Governance Lead via AI Transformation Lead |
| Weekly report in | Mon EOD before Tue governance meeting | AI Transformation Lead |
| Incident report | Within 1 hour of event | Pilot team member → AI Transformation Lead → Pilot Governance Lead |

## 9. Escalation path

| Trigger | Who notifies | Who decides | Within |
| --- | --- | --- | --- |
| Data leak, PII in prompt, case data near-miss | Pilot team → AI Transformation Lead → Pilot Governance Lead | CIO | 1 hour |
| Tool vendor breach / safety issue | AI Transformation Lead → Pilot Governance Lead | CIO + DoIT | 4 hours |
| Metric trends significantly wrong (>20% decline) | AI Transformation Lead | Pilot Governance Lead → CIO | Weekly meeting |
| Pilot team resistance / morale issue | RTE + pilot team lead → Engagement Director | Pilot Governance Lead + CIO | Next weekly |
| Scope creep request from pilot team | Pilot team → AI Transformation Lead | Pilot Governance Lead (CIO if outside authority) | Next weekly |

## 10. End-of-pilot handoff to Phase B

| # | What | When |
| --- | --- | --- |
| 1 | Pilot closes; results compiled | ~Jul 20 |
| 2 | Pilot Governance Lead presents pilot results + draft playbooks to Phase B team | Jul 20 + 1 week |
| 3 | Phase B reviews / approves / requests revisions on playbooks | First Phase B meeting |
| 4 | Scale plan approved (or revised) | First or second Phase B meeting |
| 5 | Scale begins with Phase B oversight | Next PI |

Key dependency: Phase B (full DCFS AI Governance Team) must be seated by ~Jul 1 — otherwise scale decisions slip past the pilot window.

## 11. Document artifacts (to be maintained)

| Artifact | Owner | Cadence | Location |
| --- | --- | --- | --- |
| Pilot Governance Charter (this document) | Pilot Governance Lead | As needed | Teams channel |
| Weekly meeting minutes | Pilot Governance Lead | Weekly | Teams channel |
| Risk register | AI Transformation Lead | Weekly | Internal working document |
| AI tool usage data | AI Transformation Lead | Weekly | Pulled from tool admin dashboards |
| Spot check log | Pilot Governance Lead | Weekly | Teams channel |
| Change request register | Pilot Governance Lead | Per CR | Teams channel |
| Compliance evidence | AI Transformation Lead + Pilot Governance Lead | Ongoing | Teams channel (shared tab) |
| Metrics dashboard | AI Transformation Lead | Weekly auto-refresh | Dedicated dashboard |

## 12. Sign-off

| Role | Name | Signed | Date |
| --- | --- | --- | --- |
| Executive Sponsor | Jim Daugherty (DCFS CIO) |  |  |
| Interim AI Lead | David Nika (Deputy CIO, Data Management) |  |  |
| Pilot Governance Lead | DCFS designee — TBD |  |  |
| Engagement Director | Emil "Romi" Kovacs (Krasan) |  |  |
| AI Transformation Lead | Vinay Lagisetty (Krasan) |  |  |

This charter is a working document. Update as pilot operations evolve.