## Collection Methods
Pilot Metrics — Collection Methods (V20260430)
For each metric in the proposal, this sheet describes HOW it gets collected: specific steps, level of automation, owner, cadence, prerequisites (access / tokens / labels / rubrics), estimated effort, and a feasibility flag (Confirmed / Pending / Blocked / Deferred). Take to Matt (RTE), JIRA admin, and role leads to confirm what we can actually pull and what is blocked.
Role | Metric | Data Source | Collection Method (steps) | Auto / Manual | Owner | Cadence | Prerequisites / Access | Effort per collection | Feasibility | Sample Query / Formula | Notes
Business Analyst | Story quality score (QUS 13-criteria) | JIRA stories | Pull all stories created in sprint via JQL; run script that scores each against the 13 QUS criteria | Automated | AI Transformation Lead | Per sprint | JIRA REST API token (read scope on pilot project) | ~5 min after script setup | Pending | JQL: project=ILC AND created>=startOfSprint() AND issuetype=Story | Need to confirm QUS scorer library; may need to build
Business Analyst | Acceptance criteria completeness | JIRA stories (manual sample) | Random-sample 10 stories per sprint; rate each AC block 1–5 against rubric | Manual | Pilot Governance Lead | Per sprint | JIRA read access; rubric defined | ~30 min per sprint | Confirmed |  | Rubric: clarity, testability, scope, completeness, format
Business Analyst | Refinement cycle time | JIRA transitions | JQL: stories transitioned from "Created" to "Ready for Dev"; calculate days between | Automated | AI Transformation Lead | Per sprint | JIRA REST API + changelog API access | ~5 min after script setup | Pending | GET /rest/api/3/issue/{key}/changelog | Confirm changelog API exposed
Business Analyst | Story rejection rate | JIRA workflow history | Count stories that transitioned BACK from "Ready for Dev" or later to a refinement state | Automated | AI Transformation Lead | Per sprint | JIRA REST API + changelog API | ~5 min after script setup | Pending | Filter changelog for backwards transitions
Business Analyst | SME clarification requests per story | JIRA comments / labels | Pull all comments on stories in sprint; flag those with @-mentions or "?" / "clarif" keywords | Semi-auto | AI Transformation Lead | Per sprint | JIRA REST API | ~10 min | Pending | GET /rest/api/3/issue/{key}/comment | Heuristic — may want to use a label convention instead
Business Analyst | % sprints with stories fully laid out at PI start | JIRA + PI planning records | At PI start, query: of N planned sprints, how many have all stories with story-points + AC + Ready-for-Dev? | Semi-auto | AI Transformation Lead + RTE (Matt) | Per PI | JIRA REST API + PI plan reference (Plans / Advanced Roadmaps) | ~30 min per PI | Pending |  | Talk to Matt re: Advanced Roadmaps API
Solution Architect | SDD rejection rate | SharePoint version history + ARB tracking | For each SDD, count revisions from initial submission through full ARB approval (revisions → rejections); rate = revisions per SDD | Semi-auto | AI Transformation Lead | Per SDD | SharePoint version history + ARB outcome tracking | ~10 min per SDD | Pending |  | Apr 30 team feedback: replaces "SDD revision count" — same idea, team-preferred name. Confirmed Recommended for SA.
Solution Architect | SDD creation time | Self-reported (Tempo or sheet) | SA logs hours per SDD in Tempo or shared sheet; weekly rollup | Manual | SA (self-reported) | Per SDD | Tempo or shared sheet | ~5 min per SDD | Pending |  | Apr 30 team feedback: NEED TO REVIEW before Recommended. Confirm Tempo plugin enabled; talk to Matt.
Solution Architect | SDD completeness score (pre-ARB rubric) | Manual rubric on sampled SDDs | Pre-ARB reviewer scores SDD against existing pre-ARB checklist; capture in Confluence | Manual | Pre-ARB reviewer (Shyam / Kashif) | Per SDD | Pre-ARB checklist defined | ~10 min per SDD | Pending |  | Apr 30 team feedback: NEED TO REVIEW before Recommended. Need rubric — derive from existing pre-ARB checklist.
Solution Architect | Pre-ARB cycle time | JIRA architecture-review tickets | JQL on architecture-review tickets; days from "Submitted" → "Approved" | Automated | AI Transformation Lead | Per SDD | JIRA REST API; arch-review project key | ~5 min | Pending | JQL: project=ARCH-REVIEW AND status changed to Approved | Apr 30 team feedback: "We don't track the duration" — no current baseline. Pilot establishes baseline from sprint 1 onward.
Solution Architect | ADRs logged per sprint | Confluence page-label search | Search Confluence for pages labeled "adr" created in sprint window | Automated | AI Transformation Lead | Per sprint | Confluence API token | ~5 min | Pending | GET /rest/api/content/search?cql=label=adr
Solution Architect | Maximus artifact draft time | Self-reported | Architect logs hours per Maximus-required artifact in shared sheet | Manual | SA (self-reported) | Per artifact | Shared sheet | ~5 min per artifact | Pending |  | Need list of Maximus-required artifacts (action item from Apr 16)
Solution Architect | Cross-team dependencies surfaced | JIRA epic / story link analysis | Pull issue links across teams; count dependencies surfaced per sprint | Automated | AI Transformation Lead | Per sprint | JIRA REST API | ~5 min | Pending | GET /rest/api/3/issue/{key}?fields=issuelinks
Dynamics Developer | Story cycle time (development time) | JIRA transitions | JQL: stories transitioned to "In Testing" in sprint; days from "In Progress" → "In Testing" | Automated | AI Transformation Lead | Per sprint | JIRA REST API + changelog | ~5 min | Pending |  | Apr 30 team feedback: end boundary at "In Testing" handoff (not "Done") — keeps this metric dev-only. Story-to-deploy cycle time covers full delivery cycle.
Dynamics Developer | Story-to-deploy cycle time | JIRA + Azure DevOps deploys | JIRA "Ready for Dev" timestamp + ADO deploy timestamp; calculate days | Semi-auto | AI Transformation Lead + Release Manager | Per story | JIRA API + ADO Pipelines API + release-tagging convention | ~10 min | Pending |  | Need release tagging — talk to RTE / release manager
Dynamics Developer | First-pass QA yield | JIRA transition history | Count stories where "In QA" → "Done" without going back to "In Progress" (exact JIRA workflow status names TBD) | Automated | AI Transformation Lead | Per sprint | JIRA REST API + changelog + confirmed status names | ~5 min | Pending |  | Apr 30 team feedback: OPEN — confirm exact JIRA workflow status transitions that count as "fail" trigger before locking the calculation.
Dynamics Developer | Defect density | JIRA issue links | Sum bugs linked to stories closed in sprint; divide by story points | Automated | AI Transformation Lead | Per sprint | JIRA REST API; bug-link convention | ~5 min | Pending
Dynamics Developer | Code review cycle time | GitHub REST API | Pull PRs; days from opened → merged | Automated | AI Transformation Lead | Per PR | GitHub Enterprise API token; org/repo scope | ~5 min | Pending | GET /repos/{owner}/{repo}/pulls?state=closed | Tier check (Enterprise needed for some analytics)
Dynamics Developer | Documentation coverage on PRs | GitHub PR file analysis (script) | For each merged PR, check if files in /docs/ or README* were touched | Automated | AI Transformation Lead | Per sprint | GitHub API + docs-path convention | ~5 min | Pending
Dynamics Developer | LOC delivered (plugins / APIs / logic apps) | GitHub diff statistics | Sum diff stats from merged PRs in sprint | Automated | AI Transformation Lead | Per sprint | GitHub API | ~5 min | Pending | GET /repos/{owner}/{repo}/stats/code_frequency
Dynamics Developer | % stories needing rework due to incomplete AC | JIRA transition + comment labels | Count stories returned to BA mid-sprint; require comment label "incomplete-ac" | Semi-auto | AI Transformation Lead | Per sprint | JIRA REST API + label convention | ~10 min | Pending |  | Need label convention — define before pilot
Senior Tester | Test coverage % | Zephyr Scale ↔ JIRA links | Count stories with at least one linked test case / total stories in sprint (story-level coverage) | Automated | AI Transformation Lead | Per sprint | Zephyr Scale REST API token | ~5 min | Pending |  | Apr 30 team feedback: kept at story-level (not AC-level) — easier to collect, matches existing Zephyr report. AC-level coverage moved to Discussion as future enhancement.
Senior Tester | Test cases per story | Zephyr Scale + JIRA | Count test cases linked to each story; average per story | Automated | AI Transformation Lead | Per sprint | Zephyr API | ~5 min | Pending
Senior Tester | Negative-case coverage % | Zephyr Scale + tagging | Count stories with at least one test case tagged "negative" / total stories | Semi-auto | AI Transformation Lead | Per sprint | Zephyr API + tagging convention | ~10 min | Pending |  | Need tagging convention — define before pilot
Senior Tester | Test-case authoring time | Self-reported + Zephyr timestamps | Tester logs authoring hours; cross-check with Zephyr created/updated timestamps | Manual | Tester (self-reported) | Per story | Shared sheet + Zephyr timestamps | ~2 min per story | Pending
Senior Tester | Defect escape rate | JIRA bug labels (pre-UAT vs post-UAT) | Count post-UAT bugs / total bugs in sprint | Automated | AI Transformation Lead | Per sprint | JIRA API + label convention (pre-uat / post-uat) | ~5 min | Pending |  | Confirm bug labeling convention
Senior Tester | Test-report drafting time | Self-reported | Tester logs hours to draft sprint / PI test report | Manual | Tester / TSL (self-reported) | Per sprint / per PI | Shared sheet | ~5 min per report | Pending |  | No incumbent process — pure upside
Shift-left testing (BA + Tester) | Test plan generated at story creation | JIRA + Zephyr link at story-creation timestamp | For each new story, check if a test plan was attached at story-creation time | Semi-auto | AI Transformation Lead | Per sprint | JIRA API + Zephyr API + story-creation convention | ~10 min | Pending |  | New use case — Rovo generates test plan at creation
Shift-left testing (BA + Tester) | Pre-validation test coverage % | Zephyr ↔ JIRA at validation-handoff timestamp | Compare test coverage of stories at BA-validation-handoff vs at sprint-start | Semi-auto | AI Transformation Lead | Per sprint | JIRA API + Zephyr API + handoff timestamp convention | ~10 min | Pending |  | Pairs with above
Testing Services Lead | Test automation coverage % | Zephyr Scale automation flags | % test cases marked "automated" in Zephyr (single-team for pilot) | Automated | AI Transformation Lead | Per sprint | Zephyr API | ~5 min | Pending |  | Single-team applicable; works in pilot scope
Testing Services Lead | Testing Services Playbook contributions | Confluence page history | Count of TSL-authored updates to the cross-team testing playbook in Confluence per sprint | Semi-auto | AI Transformation Lead | Per sprint | Confluence API + page-author convention | ~5 min | Pending |  | Reusable scaling artifact — TSL pilot deliverable
Testing Services Lead | Testing strategy artifacts produced | SharePoint / Confluence | Count of testing strategy / guideline documents authored or updated per sprint | Semi-auto | TSL (self-reported) + AI Transformation Lead | Per sprint | Shared sheet + SharePoint / Confluence access | ~10 min | Pending |  | Single-team applicable; complements playbook contributions
Testing Services Lead | Cross-team coverage consistency | Zephyr Scale (aggregated) | Pull coverage % per team; compute variance across the 12 teams | Automated | AI Transformation Lead | Monthly | Zephyr API for all 12 teams | ~15 min | Deferred |  | DEFERRED — activates at multi-team scale; not measurable in 1-team pilot
Testing Services Lead | Cross-team defect trends | JIRA bug data (aggregated) | Defect escape rate per team; rolling 3-month avg | Automated | AI Transformation Lead | Monthly | JIRA API for all 12 teams | ~15 min | Deferred |  | DEFERRED — activates at multi-team scale
Testing Services Lead | Cross-team test-report rollup time | Self-reported | TSL logs hours to roll up sprint / PI reports across the 12 teams | Manual | TSL (self-reported) | Per sprint / per PI | Shared sheet | ~5 min per rollup | Deferred |  | DEFERRED — activates at multi-team scale
Testing Services Lead | Cross-team pattern detection count | AI tool output + manual log | AI surfaces similar patterns; TSL logs distinct patterns identified | Manual | TSL | Monthly | AI tool access + shared log | ~30 min | Deferred |  | DEFERRED — activates at multi-team scale
Release Quality | Released-story bug return rate | JIRA bug links + release labels | For stories released in sprint N, count bugs filed within sprints N+1..N+3 / total released | Automated | AI Transformation Lead | Per sprint (trailing) | JIRA API + release labeling convention | ~10 min | Pending |  | TRAILING — needs 3+ sprints of data before first read
Release Quality | Bug-trend slope (sprint-over-sprint) | JIRA bug data (rolling window) | Plot post-release bug count over rolling 3-sprint window; compute trend slope | Automated | AI Transformation Lead | Per sprint (trailing) | JIRA API + release labeling convention | ~5 min | Pending |  | Best read after 4–6 sprints of pilot data
DORA Benchmarks | Deployment frequency | Azure DevOps pipeline history | Pull deploy events per team per sprint from ADO Pipelines | Automated | AI Transformation Lead + Release Manager | Per sprint | ADO Pipelines API access | ~5 min | Pending | GET /_apis/release/deployments | DORA core metric
DORA Benchmarks | Change failure rate | Azure DevOps deploys + JIRA incident labels | Count deploys causing incident/hotfix/rollback / total deploys | Semi-auto | AI Transformation Lead + Release Manager | Per sprint | ADO Pipelines API + JIRA incident-label convention | ~10 min | Pending |  | DORA core; needs incident labeling convention
DORA Benchmarks | Rework rate | JIRA transition history + GitHub PR re-open / re-merge | Count stories returned to earlier state + PRs reopened or amended after merge | Automated | AI Transformation Lead | Per sprint | JIRA + GitHub APIs | ~10 min | Pending |  | DORA 2025 new metric
DORA Benchmarks | AI tool ROI composite | Tool admin dashboards + estimation | Compute (prompts × acceptance × est. time saved per accept) per role per week | Semi-auto | AI Transformation Lead | Weekly rollup | Tool admin dashboards + time-saved estimation factors | ~20 min weekly | Pending |  | DORA 2025; estimation factors need calibration
Survey-derived | Pre/mid/post AI skills delta | Pilot baseline survey + mid + post | Calculate average B-block skill scores per round; diff baseline → mid → post | Manual | AI Transformation Lead | Pre / mid / post | Survey responses (3 rounds) | ~30 min per round | Pending |  | Survey v0.2 already in flight (sent Apr 29)
Survey-derived | Self-reported productivity perception | Sprint pulse + 3-round survey | Pull Likert score on productivity question; trend across rounds | Manual | AI Transformation Lead | Per sprint + 3 rounds | Survey tool | ~10 min per round | Pending
Survey-derived | Self-reported quality perception | Sprint pulse + 3-round survey | Pull Likert score on quality question; trend across rounds | Manual | AI Transformation Lead | Per sprint + 3 rounds | Survey tool | ~10 min per round | Pending |  | Pairs with measured first-pass QA yield
Survey-derived | Adoption barrier index | 3-round survey (E-block adoption barrier questions) | Aggregate E-block responses; track trend across rounds | Manual | AI Transformation Lead | 3 rounds | Survey tool | ~15 min per round | Pending |  | E1-E3 already capture this
Cross-cutting | AI tool usage volume | GitHub Copilot / Rovo / M365 admin dashboards | Weekly screenshot or CSV export from each admin dashboard | Manual | AI Transformation Lead | Weekly | Admin access to each tool dashboard | ~10 min per dashboard | Pending |  | Tier check needed — Rovo Enterprise for some breakdowns
Cross-cutting | AI suggestion acceptance rate | Tool admin dashboards | Same dashboards; pull accept/edit/reject ratios | Manual | AI Transformation Lead | Weekly | Admin access | ~5 min | Pending
Cross-cutting | Prompt-drift incidents | Incident reports + spot-check log | Pilot members log near-misses; Governance Lead reviews weekly | Manual | Pilot Governance Lead | Ongoing | Teams channel + log template | ~15 min per week | Confirmed |  | Required by DoIT AI Policy §6 + §7
Cross-cutting | SPACE survey (5 dimensions) | Survey (Survey Monkey or alt) | Distribute survey pre-pilot, mid-pilot, post-pilot; rollup scores per dimension | Manual | AI Transformation Lead | Pre / mid / post | Survey tool selected | ~30 min per round | Pending |  | Survey tool not yet chosen
Cross-cutting | AI tool satisfaction pulse | Survey | 5-question pulse survey at end of each sprint | Manual | AI Transformation Lead | Per sprint | Survey tool selected | ~10 min per round | Pending