## Slide 1
AI-Augmented Agile Delivery
Framework for DCFS Illinois Connect
Prepared for: DCFS Illinois Connect Leadership Presented by: Vinay Lagisetty & Emil "Romi" Kovacs Krasan Consulting Services Version: V20260422
CONFIDENTIAL — KRASAN INTERNAL + DCFS LEADERSHIP

## Slide 2
Illinois Connect — The Opportunity
The Program
Illinois Connect is migrating three legacy systems — SACWIS, CYCIS, and MARS — to a unified CCWIS platform on Microsoft Dynamics 365. Across 12 SAFe product teams and 160+ Krasan consultants, this ART is delivering critical capabilities for DCFS.
Why AI, Why Now
• AI is becoming standard for high-performing delivery teams
• The State has already invested in GitHub Copilot and Atlassian Rovo
• Teams are delivering well — AI builds on a strong foundation
• Krasan is developing a structured AI transformation framework — designed for engagements like ILC
Target: 10-15% productivity improvement — measured by tangible outputs, not story points. Pilot establishes the trajectory; schedule under finalization.
Amplify, Don't Replace
• Same people, better tools
• No workforce reduction
• AI assists, human decides
Measure, Don't Guess
• Baseline first, then compare
• Tangible outputs: LOC, docs, config
• Before/after with control group
Pilot, Then Scale
• Start with 1 team (Intact), 5 roles
• AI adoption from day 1 under HITL
• Scale what works
2 / 12

## Slide 3
The Framework — Krasan's Approach
Structured to work within government guardrails while delivering measurable results.
Govern
→
Baseline
→
Design
→
Train
→
Pilot
→
Measure
→
Playbook
→
Scale
PHASE | WHAT HAPPENS | DELIVERABLE
Govern | Align with DoIT AI Policy, define guardrails, confirm tool access | Governance Proposal, Compliance Map
Baseline | Capture current metrics from JIRA (last 3 sprints) | Baseline Metrics Report
Design | Map current → AI-augmented state per role; tools and methods | Process Design Docs, Playbooks, Training Plan
Train | Role-specific training: responsible AI use, prompts, guardrails | Training Completion Report
Pilot | 1 team (Intact), 5 roles for Sprints PI 6.2.1 & PI 6.2.2 | Weekly Check-in Reports
Measure | Continuous metrics; pilot vs baseline vs control | Pilot Results Report
Playbook | Codify what worked — living docs, updated continuously | Ongoing
Scale | Roll out to remaining teams based on proven results | ART-Wide Rollout Plan
3 / 12

## Slide 4
Where We Are — Govern, Baseline & Design
Govern
→
Baseline
→
Design
→
Train
→
Pilot
→
Measure
→
Playbook
→
Scale
Govern
• DoIT AI Policy — all 12 sections mapped
• NIST AI RMF governance framework
• Establish governance team (DCFS-led)
• Code generation policy — HITL compliant
Deliverable: Governance Proposal & Compliance Map
Baseline
• Capture current metrics from JIRA (last 3 sprints)
• Readiness assessment — all 12 teams
• Pilot team selected: Intact — 5 roles
• Team health survey (SPACE/DevEx)
Deliverable: Baseline Metrics Report
Design / Develop
• Map current → AI-augmented state per role
• AI-assisted code generation under HITL
• Dynamics configuration exploration
• Build training materials from process designs
Deliverable: Process Design Docs, Playbooks & Training Plan
4 / 12

## Slide 5
Train, Pilot & Measure
Govern
→
Baseline
→
Design
→
Train
→
Pilot
→
Measure
→
Playbook
→
Scale
Train
• Foundation (all): DoIT compliance, guardrails
• BA — story quality, AC generation
• Tester — test generation from AC
• Developer — code explanation, docs, refactoring
• SA — SDD, architecture, pre-ARB
• Testing Services Lead — testing strategy, cross-team
Deliverable: Training Completion Report
Pilot
• 1 team (Intact) — 5 roles
• Remaining teams as control group
• Sprints PI 6.2.1 & PI 6.2.2
• Pair programmers (1 per role) for ~2 sprints
• AI-assisted from day 1 under HITL
Deliverable: Weekly Check-in Reports
Measure
• Pre/post comparison vs baseline
• Pilot vs control teams
• 8-12 metrics across 4 families
• SPACE team health survey
• Weekly bias / quality spot checks
Deliverable: Pilot Results Report, Lessons Learned
5 / 12

## Slide 6
Playbook & Scale
Govern
→
Baseline
→
Design
→
Train
→
Pilot
→
Measure
→
Playbook
→
Scale
Playbook
Living documents — drafted in Design, refined through Pilot, v1.0 at end of pilot:
• BA Playbook — story writing, AC generation
• Tester Playbook — test generation, edge cases
• Developer Playbook — code, docs, refactoring
• SA Playbook — SDD, architecture, pre-ARB
• Testing Services Playbook — testing strategy
Deliverable: Finalized Playbooks (updated with pilot lessons)
Scale
Expand based on proven results, not assumptions.
• Go/no-go decision based on pilot data
• Pair programmers redeploy to 5 other teams (Wave 1)
• Phased rollout — not all teams at once
• DCFS AI champions embedded per role per team
• Continuous measurement at ART level
Deliverable: ART-Wide Rollout Plan
6 / 12

## Slide 7
Governance — Two-Phase Structure
Lightweight during pilot. DCFS AI Governance Team stood up DURING the pilot so they can approve results before scale.
Phase A — Pilot Governance Team
Runs the pilot · weekly 45 min · documentation over formal approval
Role | Filled by
Pilot Governance Lead | DCFS designee
Executive Sponsor | Agency CIO
Security & Privacy observer | DCFS designee (optional)
Authority: approve pilot scope, tools, guardrails. Can halt pilot on safety concern. NOT in scope: ART-wide scale decisions.
Krasan AI Transformation Lead + Engagement Director present to team; not members.
Phase B — DCFS AI Governance Team
Stood up DURING pilot · monthly 60 min · approves scale
Minimum Viable (3 seats) — start immediately
Executive Sponsor (CIO) | DCFS
AI Governance Chair (+ Program) | DCFS
Security & Privacy Lead | DCFS
Expanded (adds 3 seats) — as pilot matures
Program Director (split from Chair) | DCFS
Data Privacy Officer (split from Security) | DCFS
Business Representative | DCFS
⚠ Key dependency: Phase B team should be seated by July so they can review pilot results + approve playbooks at end of pilot. If not seated in time, scale decisions slip.
Aligned with NIST AI RMF GOVERN 2 + DoIT AI Policy §4
7 / 12

## Slide 8
Tools — Existing Investment + Pending Confirmations
✅ Already invested by the State
Tool | Primary roles
GitHub Copilot | Developer (plugins, APIs, logic apps)
Atlassian Rovo | BA, Tester — story/test drafts
Copilot supports multiple models (OpenAI, Google, Anthropic) — approval status needs validation with DCFS / DoIT.
⏳ Pending confirmation
Tool | Why we need it
Microsoft 365 Copilot | SA — SDD, Word, Visio, SharePoint
Dynamics 365 Copilot | Platform Dev — config-first workflow
Needed before pilot start to enable SA + Platform Dev tracks
Open questions we need answered
Question | Why it matters
GitHub Copilot tier (Business / Enterprise)? | Only Business/Enterprise keeps code out of training
Atlassian Rovo tier? | Lower tiers are orchestration-only; BA/Tester tracks need generative
Microsoft 365 Copilot licensed + available to pilot? | Need DCFS licensing + budget confirmation
Dynamics 365 Copilot enabled in Dynamics GCC? | Platform Dev track depends on this
§5e: Copilot on ILC source = "State data for AI"? | Determines if Agency Head written consent required
Which AI models (OpenAI, Google, Anthropic) State-approved? | Enterprise admin sets model policy
⚠ Risk / dependency: Tool access must be confirmed and provisioned before Design & Develop can start. Any delay cascades into training and pilot start.
8 / 12

## Slide 9
Timeline — PI 6 Pilot Plan
Anchored to PI 6 Planning on May 5. Govern & Design phases run in parallel before PI starts.
Phase | Apr 14 | Apr 28 | May 12 | May 26 | Jun 9 | Jun 23 | Jul 7 | Jul 21 | Aug 4 | Aug 18 | Sep 1
PI Cadence |  | PI Plan | 6.2.1 | 6.2.2 | 6.2.3 | 6.2.4 | 6.2.5 | Post-pilot |  |  | 
Govern | DoIT policy, tool access |  |  |  |  |  |  |  |  |  | 
Baseline | JIRA metrics, survey |  |  |  |  |  |  |  |  |  | 
Design |  | Process mapping, playbook drafts |  |  |  |  |  |  |  |  | 
Train |  |  | 5 role tracks |  |  |  |  |  |  |  | 
Pilot |  |  |  | Intact — Sprint PI 6.2.1 → PI 6.2.5 |  |  |  |  |  |  | 
Measure |  |  |  | Continuous metrics + before/after |  |  |  |  |  |  | 
Playbook |  | Drafted → |  | refining → |  |  |  |  | v1.0 in Aug |  | 
Scale |  |  |  |  |  |  |  |  |  | Scale decision | 
Pilot scope (draft): Intact team, 5 roles. Team composition will be finalized after the baselining phase.
9 / 12

## Slide 10
Pair-Programmer Strategy — For Discussion
5 AI-experienced specialists (one per pilot role) accelerate the pilot — then redeploy as embedded AI specialists into 5 other teams to enable scale. Same hiring investment, used twice. Proposed model — open for DCFS feedback.
Phase 1 — Pilot (May → Jul)
5 specialists × 1 Intact pilot team
Role | Pair programmer
Tester | AI-experienced Tester
Solution Architect | AI-experienced SA
Business Analyst | AI-experienced BA
Developer | AI-experienced Dev
Testing Services Lead | AI-experienced testing lead
Sprints PI 6.2.1–6.2.2 (co-pilot): Work side-by-side. Sprints PI 6.2.3–6.2.5 (coach): DCFS member owns work, specialist advises.
Phase 2 — Scale Wave 1 (Aug onward)
Same 5 specialists × 5 other ILC teams = scale mechanism
Team | Embedded AI specialist
Team 2 | 1 specialist (rotates through role)
Team 3 | 1 specialist
Team 4 | 1 specialist
Team 5 | 1 specialist
Team 6 | 1 specialist
~2 sprints per team, then rotate. Output: each team finishes with named internal DCFS AI champion per role.
Exit strategy: Specialists rotate out team by team. 30+ DCFS internal AI champions by end of Wave 1; consultants phased out.
Why this matters: Same pilot hiring investment becomes the scale mechanism. Playbooks battle-tested across 6 teams, not just 1.
⚠ Key constraint: Finding the right AI-experienced specialists is difficult. Hiring velocity is a real risk — stair-step onboarding is the mitigation.
10 / 12

## Slide 11
Risks — What Could Derail Us
Top risks actively managing. Flagging for awareness; asking DCFS for any risks (audits, release freezes, Maximus reviews, leadership) we have not captured.
Risk | Lik. | Imp. | Mitigation in progress
DoIT 30-day notice delays pilot start | Unknown | High | Template + owner + parallel-work determination in this meeting
Tool access not in place before Design & Develop (Copilot tier, M365/D365 Copilot) | High | High | Close 6 tool questions this week; fallback to sequenced training
§5e ambiguity — Copilot on source = "State data for AI"? | Medium | High | Written determination requested from DCFS interim AI lead
Pair-programmer hiring velocity — 5-6 external hires needed | Medium | Medium | Stair-step onboarding; start with 1-2 roles; Krasan bench in progress
10-15% target on config-first platform — ambitious, small sample | Medium | Medium | Frame as trajectory; 2-PI full adoption; measure trends not absolutes
V3 workflow transition is a measurement confound | Medium | Medium | Freeze Intact workflow, or record state alongside each measurement
State pulls AI tools mid-pilot (CMS Oct 2025 precedent) | Medium | Critical | Full DoIT + NIST compliance upfront; documentation first-class
Sensitive data in AI prompts (PII, case data) | Low | Critical | "No PII" training; per-sprint spot checks; incident reporting path
Full risk register (20+ items with owners + status) in planning/deliverables/assumptions-and-risks.md. Reviewed weekly in Pilot Governance meetings.
Ask for DCFS: Any risks we have not captured? Production release freeze, Maximus audit window, leadership transitions, federal reporting deadlines?
11 / 12

## Slide 12
Discussion & Next Steps
Target: 10-15% productivity improvement — tangible outputs, not story points Scope: Pilot team = Intact, 5 roles (draft — confirmed after baselining) Approach: AI-assisted work from day 1 under mandatory Human-in-the-Loop review
What we need from DCFS
🔴 This week — pilot blockers
• §5e written determination (Copilot on source = State data?)
• Tool availability (6 questions confirmed)
• DoIT 30-day notice template + owner
🟡 This month
• Pilot Governance Lead — DCFS designee
• Security & Privacy observer (optional)
• Clearance process + timeline for pair-programming AI specialists
Krasan drives execution. DCFS provides these decisions + designees.
CONFIDENTIAL — KRASAN CONSULTING SERVICES